## Treatment Plan
Risk ID | Treatment Action | Control Owner | Priority | Due Date | Success Measure | Status
FC-R01 | Implement MFA for privileged access and quarterly privileged access review. | IT Manager | Critical | 2026-10-31 | 100% privileged accounts MFA-enabled | In Progress
FC-R02 | Implement cloud configuration monitoring and secure baseline review. | Cloud Owner | High | 2026-09-30 | No high-risk public exposure findings | Open
FC-R03 | Deploy immutable backups and conduct recovery testing. | Infrastructure | Critical | 2026-11-30 | Successful recovery test within target RTO | In Progress
FC-R04 | Introduce supplier security requirements and signed-code validation. | Engineering | High | 2026-12-15 | Critical suppliers assessed | Open
FC-R05 | Enforce full-disk encryption and remote wipe. | IT Manager | Medium | 2026-09-15 | 100% managed endpoints encrypted | Planned
FC-R06 | Deploy phishing-resistant MFA and recurring awareness exercises. | Security Lead | High | 2026-10-15 | Reduced phishing simulation failure rate | In Progress